## Ark3
SEMESTER PROJECT |  |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5
|  |  | Date | 2020-08-24 | 2020-08-25 | 2020-08-26 | 2020-08-27 | 2020-08-28 | 2020-08-29 | 2020-08-30 | 2020-08-31 | 2020-09-01 | 2020-09-02 | 2020-09-03 | 2020-09-04 | 2020-09-05 | 2020-09-06 | 2020-09-07 | 2020-09-08 | 2020-09-09 | 2020-09-10 | 2020-09-11 | 2020-09-12 | 2020-09-13 | 2020-09-14 | 2020-09-15 | 2020-09-16 | 2020-09-17 | 2020-09-18 | 2020-09-19 | 2020-09-20 | 2020-09-21 | 2020-09-22 | 2020-09-23 | 2020-09-24 | 2020-09-25 | 2020-09-26 | 2020-09-27
Student: Tom Stian Fjermeros |  |  | Days | 2020-08-24 | 2020-08-25 | 2020-08-26 | 2020-08-27 | 2020-08-28 | 2020-08-29 | 2020-08-30 | 2020-08-31 | 2020-09-01 | 2020-09-02 | 2020-09-03 | 2020-09-04 | 2020-09-05 | 2020-09-06 | 2020-09-07 | 2020-09-08 | 2020-09-09 | 2020-09-10 | 2020-09-11 | 2020-09-12 | 2020-09-13 | 2020-09-14 | 2020-09-15 | 2020-09-16 | 2020-09-17 | 2020-09-18 | 2020-09-19 | 2020-09-20 | 2020-09-21 | 2020-09-22 | 2020-09-23 | 2020-09-24 | 2020-09-25 | 2020-09-26 | 2020-09-27
TASKS | START DATE | END DATE
Gantt Cart | 2020-08-24 | 2020-08-25
Research | 2020-08-26 | 2020-08-27
Target Audience | 2020-08-28 | 2020-08-29
API | 2020-08-30 | 2020-08-30
Design
Sketches | 2020-08-31 | 02.09.02.2020
Graphic Design | 2020-08-03 | 2020-09-09
HTML/CSS
Mobile Devices | 2020-09-10 | 2020-09-14
Laptop Devices | 2020-09-15 | 2020-09-19
JavaScript/API | 2020-09-18 | 2020-09-23
Test | 2020-09-17 | 2020-09-22
Report | 2020-09-24 | 2020-09-24
Delivery Day | 2020-09-27 | 2020-09-27
Resarch: look around for inspirasion for my web page
Sketches: Playing around whit different layout for the web and mobile devices, colors and use of pictures
Graphic Design: Make tamplets, color design and how the page will look
HTML/CSS: Starting dveloping the website and get it functional for laptop and mobile devices and test the website
Formulas:
Week 1 = [Week 1, row above]
Week 3 = [Week 3, row above]